## Test Plan
TEST PLAN IDENTIFER | FRONT ACCOUNTING Version -2.4.15
INDRODUCTION | Front Accounting (FA) is a professional web - based Accounting system for Enterprise Resource Planning(ERP). it is developed in php /Ajax using MYSQL: management system. it is targeted towards small and medium sized enterprises. it is integrated with modules that support most commom bussiness process. Front Accounting is multi-user system. it supports mutiple languages and currencies . Front Accounting is developed by an internationalteam . Senior developed joe hunt from sweden and janusz Dobrowolski from poland
REFERENCES | front Accounting user guide manual .pdf
TEST ITEMS | A)Login: in the login page the user have to login using your valid user id and password . Mutiple users can login into system B)sales: in the sales module . the seller/ salesman can setup a quotation entry and after that itcan be convert into sales order entry if there is an order for product from customer's side . Then the salesman can make a delivery entry for the products which is been dispatched to customer along with an invoice entry. After the customer does payments the salesman can make a customer payments entry in the system for the same C)purchases: in the purchase module, the Buyer makes a purchase order entry in the system for the products he/she ordered to the supplier. the buyer can make goods recive entry for products that has been deliverd from supplier along with a supplier invoice entry . then the buyer can make a supplier entry after paying the desired amount for the products they recived D)items and inventory:in the item and invertory module, here the stockist / invertory manger maintain the goods/products which are allocated at different warehouses in different locations,here they maintain the record of goods transferred from one location to another location with a specific date .Here they also maintain the status of each products at differnt location warehoues and the transation deatils of each products with a specfic date range / duration
FEATURES TO BE TESTED | a)Login: user login b) sales: 1.sales Quotation entry: 1.1 place quotation entry 1.2 cancel quotation entry 2.sales order entry : 2.1 place order entry 2.2 cancel order entry 3.delivery for sales order; 3.1update the order details 3.2 clear quantity 3.3process dispatch 4. invoice for delivery note; 4.1 process invoice 4.2 update invoice 5.customer payment; 5.1 add payement entry C)purchase: 1.purchase order entry ; 1.1place order entry 1.2 cancel order entry 2. Recive purchase order items(RPOI) 2.1 update purchase order 2.2 process receive items 3.supplier invoice entry ; 1. enter invoice 4.payment to supplier : 4.1 enter supplier payment D)item and invertory : 1.inventory location Trasfer 1.1process transfer
FEATURES NOT TO BE TESTED | a) manufacturing b)Fixed Assets c)Dimensions d)Banking and General ledger e) setup
TEST ENVIRONMENT | Hardware RAM -8gb processor-intel i5 core processor with 3GHz Operating System-Windows, Linux Server-Apache Tomcat Browsers- Google chrome ,Mozilla Firefox Software: pdf Reader- Adode pdf reader Jira- Defect Tracking Tool
TEST APPROCH | A) method of Testing 1.black- Box Testing method 2. smoke testing B)Levels of Testing : 1.System integration Testing(SIT) 2.Regression Testing C)Types of Testing: 1.functional testing- with the scope - flows 2.compatibility Testing 3.security Testing 4.performance Testing 5.Cross Browser Testingin (chrome & firefox)
TEST DELIVERABLES | A)test plan B)test scenarios C) test cases D) Defect Summary Report/ Daily status Report E)issue Logs
SUSPEND AND RESUME CRITERIA | SUSPEND CRITERIA RESUME CRITERIA 1) show stopped defect 1)shows stopped defect is resloved and retested found(Bolcker defect) 2)power outages 2)power issue is resolved 3)system has crashed 3)system(hardware / software is fixed and can be resumed)
ITEM PASS / FAIL CRITERIA | TEST EXIT Criteria : (item pass / fail criteria) 1) All the test Cases should be executed (with 100% Test Coverage) 2)All the test cases should be with pass status post test execution 3)Code for all failded testcases should be fixed / Retested and closed 4)Required quality of product (software) should be achieved 5)All the test Deliverables should be updated with latest Content
RISK AND CONTENGENCIES | 1. Non- availability of complete "Test Basic" 2. Delay in receiving the build from Development Team 3.lack of required testing resource to complete the test on time
SOFTWARE RISK ISSUE | 1.Non -availability of test automation tools to test 2.Non availability of functionally skilled Testers to test the functional product 3.Non availability of training on the product to the testers
ROLES AND RESPONSIBITIES | SR.NO Designation Task/Activities 1Devesh Pandey Manual Tester Test plan Writing 2Devesh Pandey Manual Tester Test senarios Writing 3 Devesh Pandey Manual Tester Test senarios writhing 4 Devesh pandey Manual Tester Test case writhing/ Execution & Defect Reporting 5 Devesh pandey Manual Tester Test case Writhing/ Execution & Defect Reporting 6 Devesh pandey Manual Tester Test case Writhing / Execution & Defect Reporting
SCHEDULE | Sr.No Task / Activities Days Date Range 1 Test Plan Writing 2 Test Senarios Writhing 3 Test Case Writhing 4 Test Case Execution & Defect Reporting
STAFFING | Training Conducted By: Training Conducted For Training Topic 1) Functional Walkthru & training of Front Accounting (ERP) application Functional flows of belows Modules : a) sales b) purchases c)invertory & its sub- modules Prashant S Devesh Pandey 2)Training of jira tool to login defects (issues) found during test execution by testing team 3)Software testing process walkthru for team to follow common test standards ast Quastech
APPROVAL | Sr.No Name of the person Designation / role Date Remark (Approved / unapproved) Signature 1 Ranjini Mam Test Manager 18/10/26 Approved 2 Ranjini Mam Test Manager 18/10/26 Approved 3 Ranjini Mam Development Manager 18/10/26 Approved 4 Ranjini Mam Business Analyst 18/10/26 Approved 5 Ranjini Mam Sponsor 18/10/26 Approved

## Decision Tables
Add irem | case1 | case2 | case3 | case4
item code | Negative | positive | positive | positive
quantity | positive | negative | positive | positive
price | positive | positive | negative | positive
discount | positive | positive | positive | negative
Result | Error msg / default value | Error msg / Default value | Error msg / Default value | Add item
Decision table on edit item
edit item | case1 | case2 | case3 | case4
quantity | positive | negative | positive | negative
discount | positive | positive | negative | negative
result | edit item | error msg/ deafult value | error msg / deafult value | deafult value / error msg
Decision table on Placed Quotation
Condition | case1 | case2 | case3 | case4 | case5 | case 6 | case 7 | case 8
quotation date past | positive | negative | negative | negative | negative | negative | negative | positive
quotation date present | negative | postive | negative | negative | negative | negative | negative | positive
quotation date future | negative | negative | positive | negative | negative | negative | negative | negative
add item | negative | negative | negative | positive | negative | negative | negative | positive
delivery details vaild | negative | negative | negative | negative | positive | negative | negative | positive
delivery details invaild | negative | negative | negative | negative | negative | positive | negative | negative
result | error msg | error msg | error msg | error msg | error msg | error msg | error msg | placed quotation
decision table on cancel quotation
Condition | case1: case1; case2: case2; case3: case3; case4: case4
Quotation form | case1: valid enterd data; case2: valid enterd data; case3: valid enterd data; case4: valid enterd data
cancel button | case1: clicked; case2: click; case3: not click; case4: click
confirmation | case1: ok clicked; case2: not click; case3: not click; case4: ok click
result | case1: Quotation form cleared; case2: Quotation form remains; case3: No action; case4: Form cleared
1) create company managed project
2) goto -> apps --> explore apps
search x ray bar test management
add free trial
3) apps --> > x- ray
> cofigure project
> select company manage
> summary
-- add issue types
4) check issues types
test
testcases
pre-condition
and so on
what is api testing
what web servivers
arch of api testing( layers)
rest api and soap
what the https status code ( image)
request videos
get / post / put /patch / delete
assegioin

## Test Scenario
Section 1
Module 1:- New Sales Quotation Entry
Test scenario I'd | name / objective | pre-condition | Test condition
Sc_01 | Add item | logged in,Url, Browser,Internet Active | To test item get add when Item code is enterned negative and quantity,price,dicsount are are positive
To test item get add when quantity is enterned negative and add code,price,dicsount are are positive
To test item get add when price is enterned negative and add code,quantity,dicsount are are positive
To test item get add when discount is enterned negative and add code,quantity,price are are positive
To test item get add when item code,quantity ,price ,discount is positive
Sc_2 | edit item | logged in,Url, Browser,Internet Active ,user logged | to test item get edit when quantity and discount are positive
to test item get edit when quantity and discount are negative
to test item get edit when quantity is postive and discount is negative
to test iten get edit when quantity is negative and discount is positive
Sc_03 | delete item | logged in,Url, Browser,Internet Active ,user logged ,item added | to test single item get delete when click on delete button
to test mutiple item get delete when click on delete button
Sc_04 | updated item | logged in,Url, Browser,Internet Active ,user logged ,item added | to test item get updated when total amount calculate and shipping charge is invalid
to test item get updated when total amount calculate and shipping charge is valid
to test item get updated when total amount calculate and shipping charge is blank
Sc_05 | back button | logged in,Url, Browser,Internet Active ,user logged ,item added | to test the when clicked on back navigate on perivous module
To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged
Sc_06 | placed quotation | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | to test quotation gets placed when current quotation date of "" valid until"" section in quotation delivery details is selected
to test quotation gets placed when past quotation date of "" valid until"" section in quotation delivery details is selected
to test quotation gets placed when future quotation date of "" valid until"" section in quotation delivery details is selected
to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is valid
to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is invalid
to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is blank
to verify quotation gets placed when valid date such as persent and future date to place quotation
Sc_07 | cancel Quotation | logged in,Url, Browser,Internet Active | To test if the quotation is cancelled when Cancel Quotation is clicked and OK is selected
To test if the quotation is cancelled when Cancel Quotation is clicked and Cancel is selected.
To test if the quotation remains unchanged when Cancel Quotation is not clicked.
Module 2 :- Sales Order Entry
Sc_08 | Add more Item | logged in,Url, Browser,Internet Active ,New sales quotataion Entry should placed | To test or verify that the mutiple items can be added or not in sales order entry .
Sc_09 | Delete item | logged in,Url, Browser,Internet Active ,New sales quotation Entry should placed | Refer to Sc_03
Sc_10 | Edit item | logged in,Url, Browser,Internet Active ,New sales quotation Entry should placed | Refer to Sc_02
Sc_11 | Place Order | logged in,Url, Browser,Internet Active New sales quotation Entry should placed | Refer to Sc_06
Sc_12 | Cancel Order | logged in,Url, Browser,Internet Active ,New sales quotation Entry should placed | Refer to Sc_07
Sc_13 | Back | logged in,Url, Browser,Internet Active ,New sales quotation Entry should placed | Refer to Sc_05
Module 3 :- Deliver Items for a Sales Order
Sc_14 | Delivery From | logged in,Url, Browser,Internet Active ,order should be placed. | To test or verify user can select valid Delivery from section when click by the user
Sc_15 | Shipping Company List | logged in,Url, Browser,Internet Active ,order should be placed. | To test or verify that the Shipping Company list is displayed Valid when accessed by the user.
Sc_16 | This Delivery | Login, URL, Browser, Internet active,order should be placed | 1. To test or verify This Delivery gets updated when a valid value is entered
2. To test or verify This Delivery when an invalid/blank/negative value is entered.
3. To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Automatically put balance on back order”.
4To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Cancel any quantities not delivered”.
Sc_17 | Date | Login, URL, Browser, Internet active,order should be placed | To test or verify Deliver Items for a Sales Order date is future date
To test or verify Deliver Items for a Sales Order date is past date
To test or verify Deliver Items for a sales oder default value of delivery entry date
Sc_18 | process dispatch Button | Login, URL, Browser, Internet active,order should be placed | To test or verify the process dispatch when valid Data are entered.
To test or verify the process dispatch when lnvalid/Blank Data are entered.
Sc_19 | Back button | Login, URL, Browser, Internet active,order should be placed | Refer to Sc_05
Sc_20 | update button | Login, URL, Browser, Internet active,order should be placed | Refer to Sc_04
Sc_21 | Clear quantity & reset Quantity button | Logged in, browser active, valid Sales Order with delivery item | To test Clear Quantity sets This Delivery quantity to 0 and sets Total, Sub-total, Included Tax and Amount Total to 0.
|  | Logged in, browser active, valid Sales Order with delivery item | To test Reset Quantity sets This Delivery quantity equal to Ordered quantity and recalculates Total, Sub-total, Included Tax and Amount Total accordingly.
To test the Clear Quantity button is renamed to Reset Quantity after clearing the delivery quantity.
Module 4-Issue an Invoice for Delivery Note
Sc_22 | Process invoice- to verify process invoice functionality | 1. User is logged in to the application. 2. Valid delivery/invoice details are available for processing. 3. Required customer and item details are available. 4. User is on the Process Invoice screen. | test or verify that the Invoice Date is populated with the current/system date, allows a past date, and does not allow a future date.
To test or verify that the user can select the required Payment Terms from the available options.
.To test or verify that the Due Date is calculated correctly based on the selected Payment Terms and Invoice Date.
test or verify that clicking Process Invoice successfully processes the invoice and creates the required dispatch entry
Sc_23 | to verify the Reference functionality | Login, URL, Browser, Internet active. | To test or verify that the Reference is displayed for the invoice.
To test or verify that the Reference is automatically generated for the invoice
Sc_24 | Back | Login, URL, Browser, Internet active. | refer to sc_05
Sc_25 | update | Login, URL, Browser, Internet active. | refer to sc_04
Module 5 - Customer Payment Entry: Field Description
Sc_26 | Date of Deposit | Customer Payment Entry screen is open | To test or verify that Date of Deposit is populated with the system date by default.
To test or verify that Date of Deposit represents the date on which payment was deposited.
To test or verify that Date of Deposit can be changed from the default system date to the payment deposit date.
Sc_27 | Bank Charge | Customer Payment Entry screen is open | To test or verify that Bank Charge can be entered when charges are levied by the bank.
To test or verify that the entered Bank Charge is mentioned in the Bank Charge field.
o test or verify that Bank Charge is captured for the payment transaction.
Sc_28 | Amount of Discount | Customer Payment Entry screen is open. | To test or verify that Amount of Discount can be entered when a discount is offered to the customer.
To test or verify that the entered Amount of Discount is considered for the payment amount.
To test or verify that Amount displays the final amount after deduction of the discount amount.
Sc_29 | Amount | Customer Payment Entry screen is open with invoice details available | To test or verify that Amount displays the amount as per the invoice.
to test or verify that Amount displays the final amount after deduction of the discount amount.
Sc_30 | Add Payment | Customer Payment Entry details are entered. | to test or verify that Add Payment button is available to submit the customer payment.
To test or verify that clicking Add Payment makes a successful Payment Entry to the customer.
To test or verify that the entered payment details are submitted through Add Payment.
Sc_31 | Reference | Login, URL, Browser, Internet active. | Refer to sc_23
Sc_32 | back | Login, URL, Browser, Internet active. | Refer to sc_05
Section 2
Module 6 - Purchase Order Entry
Sc_33 | Supplier & Receive Into | URL and Intetrnet Active, Browser Working, Register user | To test or verify user can select required Valid section when value is correctly dropdown
Sc_34 | Supplier's Reference | URL and Intetrnet Active, Browser Working, Register user | To test or verify that the user can enter Valid alphanumeric Reference value
To test or verify that the user can enter Blank Reference value
Sc_35 | Deliver to | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify user enter valid address
2) To test or verify user enter Blank/Invalid address
Sc_36 | Add item | URL and Intetrnet Active, Browser Working, Register user | To test item get add when Item code is enterned negative and quantity,price,required delivery date are are positive
To test item get add when quantity is enterned negative and add code,price,required delivery date are are positive
To test item get add when price is enterned negative and add code,quantity,required delivery date are are positive
To test item get add when required delivery date is enterned negative and add code,quantity,price are are positive
To test item get add when item code,quantity ,price ,required delivery date is positive
Sc_37 | Edit item | URL and Intetrnet Active, Browser Working, Register user ,add item | to test item get edit when quantity and required delivery date are positive
to test item get edit when quantity and required delivery date are negative
to test iten get edit when quantity is negative and required delivery date is positive
to test item get edit when quantity is postive and required delivery date is negative
Sc_38 | Delete item | logged in,Url, Browser,Internet Active ,user logged ,item added | to test single item get delete when click on delete button
to test Mutiple item get delete when click on delete button
Sc_39 | order Date | Login, URL, Browser, Internet active | To test or verify Purchase Order Entry date is future date
To test or verify Purchase Order Entry date is default date or past date
Sc_40 | Place order button | Login, URL, Browser, Internet active | To test or verify the place order get placed when valid Data are entered.
To test or verify the process for dispatching selected item when lnvalid/Blank Data are entered.
Sc_41 | Cancel order buton | URL and Intetrnet Active, Browser Working, Register user | To test or verify the Cancel order button should clear the page and displayed back
To test or verify the Cancel order button should not clear the page and not navigate back module
Sc_42 | Back | logged in,Url, Browser,Internet Active ,user logged ,item added | to test the when clicked on back navigate on perivous module
To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged
Module 7 - Receive Purchase Order Items
Sc_43 | update | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify can update This delivery data when Quantity is Equal or less then Ordered unit
To test or verify can update This delivery data when Quantity is Blank or More then Ordered unit
Sc_44 | Process Receive Item | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify the Purchase get Processed when valid Data are entered
2) To test or verify the Purchase get Processed when Invalid/Blank Data are entered
Sc_45 | Back | logged in,Url, Browser,Internet Active ,user logged ,item added | Refer to Sc_42
Sc_46 | This Delivery | Login, URL, Browser, Internet active,order should be placed | 1. To test or verify This Delivery gets updated when a valid value is entered
2. To test or verify This Delivery when an invalid/blank/negative value is entered.
3. To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Automatically put balance on back order”.
4To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Cancel any quantities not delivered”.
Module 8 - Enter Supplier invoice
Sc_47 | Quantity Items Received for invoice | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify the user can enter "Qty Yet To Invoice" is equal or less than "Quantity Received"
2) To test or verify the user can enter "Qty Yet To Invoice" is Blank/Negative/ More than "Quantity Received"
Sc_48 | Enter Invoice button | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify the Purchase Invoice get Processed when valid Data are entered
2) To test or verify the Purchase Invoice get Processed when Invalid/Blank Data are entered
Sc_49 | Add All Item | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify user can add all the Purchase items at once.
Sc_50 | Tax and Update Button | URL and Intetrnet Active, Browser Working, Register user | 1)To test or verify Total amount gets calculate correctly when user add valid Tax charge
2)To test or verify Total amount gets calculate correctly when user add Invalid/Blank/Negative shipping Tax
Sc_51 | Supplier's Reference | URL and Intetrnet Active, Browser Working, Register user | Refer to Sc_34
Sc_52 | update | URL and Intetrnet Active, Browser Working, Register user | Refer to Sc_43
Sc_53 | Back | logged in,Url, Browser,Internet Active ,user logged ,item added | Refer to _42
Module 9 - Supplier Payment Entry
Sc_54 | Bank Amount | URL and Intetrnet Active, Browser Working, Register user | 1) Test or verify user can enter Valid Bank amount when select retailer
2) Test or verify user can enter Blank/Negative/Invalid Bank amount when Customer is Retailer
Sc_55 | This Allocation | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify This allocation display correctly when user click on All link the total amount of field will be show
2) To test or verify This allocation feild when user enter Invalid/Negative/Blank values
Sc_56 | None | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify This allocation field gets Blank when user click on None Button
Sc_57 | Amount of Discount | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify user can add discount in "Amount of Discount" when valid value will be enter
2) To test or verify user can add discount in "Amount of Discount" when Blank/Invalid/Negative value will be enter
Sc_58 | Amount of Payment | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify user can add or enter valid Payment amount value
2) To test or verify user can add or enter Invalid/Blank/Negative Payment amount value
Sc_59 | Enter a Payment Button | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify the Payment get placed when valid Payment Amount, Bank charges,This allocation , Amount and Discount are entered.
2) To test or verify the Payment get placed when Invalid/Blank Payment Amount, Bank charges,This allocation , Amount and Discount are entered.
Section 3
Module 10- Inventory Location Transfers: Field Description
SC_60 | Date | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify date is accepted when Past date & Present date should be selected
2) To test or verify date is accepted when Future date should be selected
Sc_61 | From Location & To Location | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify user can select differenet selection for From location & To location data
2) To test or verify user can select same selection for From location & To location data
Sc_62 | Items | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify Item gets add when Item code, Item Description, Quantity entered valid
2) To test or verify Item gets add when Item code is kept Invalid/Blank/Negative and Item Description, Quantity entered valid
3) To test or verify Item gets add when Item Description is kept Invalid/Blank/Editable and Item code, Quantity entered valid
4) To test or verify Item gets add when Quantity is kept Invalid/Blank/Negative and Item code, Item Description entered valid
Sc_63 | Process Transfer | URL and Intetrnet Active, Browser Working, Register user | 1) To test or verify the Process Transfer get Processed when valid Data are entered
2) To test or verify the Process Transfer get Processed when Invalid/Blank Data are entered
Sc_64 | back | URL and Intetrnet Active, Browser Working, Register user | to test the when clicked on back navigate on perivous module
To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged

## test case
Sales Quotation Entry Test Case
Add item
Test case id | objective | Pre-condition | stepid & Desc | input data | Expected data | Actual Result | Status | Remark
Sc_01-tc_01 | To test item get add when Item code is enterned negative and quantity,price,dicsount are are positive | logged in,Url, Browser,Internet Active | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item | -22222 iPad Air 2 16GB 1 300 5% --> | Item should not add and shows error message"" "Invalid Item Code or Description Entered"" | Application Doesn't show Error Message | fail
Sc_01-tc_02 | To test item get add when quantity is enterned negative and add code,price,dicsount are are positive | logged in,Url, Browser,Internet Active | 1.Enter a Item code 2.Select a item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item | 101 iPad Air 2 16GB 1!@$$ 300 5% --> | Quantity should be not added and shows Default value""Quantity shows the 0 value"" | Application should display Error Message "The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100." | Pass
Sc_01-tc_03 | To test item get add when price is enterned negative and add code,quantity,dicsount are are positive | logged in,Url, Browser,Internet Active | 1.Enter a Item code 2.Select a item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item | 101 iPad Air 2 16GB 21 !@#$%^ 4% --> | price should be not added it's show the actual price item"" Its shows the default value"" | "Application should display Error Message ""Price 0.00 is below Standard Cost 297.35""" | Pass
Sc_01-tc_04 | To test item get add when discount is enterned negative and add code,quantity,price are are positive | logged in,Url, Browser,Internet Active | 1.Enter a Item code 2.Select a item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item | 101 iPad Air 2 16GB 21 300 2!3% --> | Discount should not be added shows error message "" quantity ordered to less than 0, or the discount percent to more than 100."" | "Application should display Error Message ""The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100.""" | Pass
Sc_01-tc_05 | To test item get add when item code,quantity ,price ,discount is positive | logged in,Url, Browser,Internet Active | 1.Enter a Item code 2.Select a item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item | 101 iPad Air 2 16GB 1 300 5% --> | Item should be add Successfully | same as expected result | Pass
Edit item
Sc_02-tc_01 | to test item get edit when quantity and discount are positive | logged in,Url, Browser,Internet Active ,user logged | 1 click on Edit button 2.Enter a Quantity 3.Enter a Discount 4.Click on confirm Change | Quantity-11 Discount-10% | Item should be edit successfully | same as expected result | Pass
Sc_02-tc_02 | to test item get edit when quantity and discount are negative | logged in,Url, Browser,Internet Active ,user logged | 1 click on Edit button 2.Enter a Quantity 3.Enter a Discount 4.Click on confirm Change | Quantity-@!# Discount-@!@$%23% | item should not be edit add quantity and dicsount it's show the ""The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100."" | Price for inventory item must be entered and can not be less than 0 | Pass
Sc_02-tc_03 | to test item get edit when quantity is postive and discount is negative | logged in,Url, Browser,Internet Active ,user logged | 1 click on Edit button 2.Enter a Quantity 3.Enter a Discount 4.Click on confirm Change | Quantity- 23 Discount-@!@$%23% | Item should be not edit a discount it's show the "" the discount percent to more than 100."" | The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100. | Pass
Sc_02-tc_04 | to test iten get edit when quantity is negative and discount is positive | logged in,Url, Browser,Internet Active ,user logged | 1 click on Edit button 2.Enter a Quantity 3.Enter a Discount 4.Click on confirm Change | Quantity- !@#$%23 Discount-5% | item should not be edit a quantity it's show the "" quantity ordered to less than 0"" | The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100. | Pass
Delete item
Sc_03-tc_01 | to test single item get delete when click on delete button | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.click on delete ""X bar icon"" | Sales Quotation Items | Item should be delete successfully | same sa expected result | Pass
Sc_03-tc_02 | to test mutiple item get delete when click on delete button | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.click on delete ""X bar icon"" | Sales Quotation Items | item should be not delete multiple item | same as expected result | fail
Updated item
Sc_04-tc01 | to test item get updated when total amount calculate and shipping charge is invalid | logged in,Url, Browser,Internet Active ,user logged ,item added | 1. click on update button 2.total amount calculated 3Enter a shipping charge 4.Enter a update button | Enter Shipping charges !@#$%^ Click on update Button | item should be not update show ""error message"" | Application Doesn't show Error Message | Fail
Sc_04-tc02 | to test item get updated when total amount calculate and shipping charge is valid | logged in,Url, Browser,Internet Active ,user logged ,item added | 1. click on update button 2.total amount calculated 3Enter a shipping charge 4.Enter a update button | Enter Shipping charges- 23 Click on update Button | item should be update successfully | Application should display "Shipping charges added successfully." | pass
Sc_04-tc03 | to test item get updated when total amount calculate and shipping charge is blank | logged in,Url, Browser,Internet Active ,user logged ,item added | 1. click on update button 2.total amount calculated 3Enter a shipping charge 4.Enter a update button | Enter Shipping charges- "" "" Click on update Button | item should be update successfully | Application Doesn't show Error Message | Fail
Back button
Sc_05-tc01 | to test the when clicked on back navigate on perivous module | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.Click on "Back" Button | --> | Application should be navigate perivous page | same as expected result | Pass
Sc_05-tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.Click on "Back" Button | --> | Application should be same page not navigate the previous page | Application should display blank data | Pass
Placed Quotation button
Sc_06-tc01 | to test quotation gets placed when current quotation date of "" valid until"" section in quotation delivery details is selected | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery details 2. click on Calender icon button 3.Select Valid Until Date | 2026-10-04 | Quotation should be placed successfully. | same as expected result | Pass
Sc_06-tc02 | to test quotation gets placed when past quotation date of "" valid until"" section in quotation delivery details is selected | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery details 2. click on Calender icon button 3.Select Valid Until Date | 2026-10-02 | Error/validation message should be displayed for the past quotation date and quotation should not be placed | The quotation was not placed; a quotation-date validation message was displayed. | Pass
Sc_06-tc03 | to test quotation gets placed when future quotation date of "" valid until"" section in quotation delivery details is selected | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery details 2. click on Calender icon button 3.Select Valid Until Date | 2026-10-08 | Error/validation message should be displayed for the future quotation date and quotation should not be placed. | Application Doesn't show Error Message | fail
Sc_06-tc04 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is valid | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery detail 2.Enter valid Deliver To, Address, and Contact Number. | Deliver To: ABC Company Address: pune, Maharashtra contact no.:9876543210 | Valid quotation details are accepted. | same as expected result | Pass
Sc_06-tc05 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is invalid | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery detail 2.Enter valid Deliver To, Address, and Contact Number. | Deliver To: !@3 Company Address: !@#$%^&*( contact no.:!@#$%^&*() | Application should display Error Massage | The quotation was not placed; delivery/address validation messages were displayed. | Pass
Sc_06-tc06 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is blank | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid | 1. select a Quotation Delivery detail 2.Enter valid Deliver To, Address, and Contact Number | Deliver To :"" "" Address:"" "" contact no.: "" "" | Application should display "You must enter the person or company to whom delivery should be made to" “You should enter the street address in the box provided. Orders cannot be accepted without a valid street address. "contact number must be a valid 10-digit number" | Application Doesn't show Error Message | Fail
Sc_06-tc07 | to verify quotation gets placed when valid date such as persent and future date to place quotation | logged in,Url, Browser,Internet Active, item added,Quotation Entry,should be valid quotation delivery details should be valid | 1. select a quotation date 2. enter a valid date | 2026-04-01 | Quotation should be placed successfully. | same as expected result | Pass
Cancel Quotation
Sc_07-tc01 | To test if the quotation is cancelled when Cancel Quotation is clicked and OK is selected | logged in,Url, Browser,Internet Active | 1.click on cancel quotataion 2. confirmation OK | Cancel Quotation: Clicked Confirmation: OK | Quotation should be cancelled successfully. | Quotation was cancelled successfully after clicking Cancel Quotation and selecting OK. | Pass
Sc_07-tc02 | To test if the quotation is cancelled when Cancel Quotation is clicked and Cancel is selected. | logged in,Url, Browser,Internet Active | 1.click on cancel quotataion 2. confirmation Cancel | Cancel Quotation: Clicked Confirmation:cancel | Quotation should remain unchanged. | Quotation remained unchanged after clicking Cancel Quotation and selecting Cancel | Pass
Sc_07-tc03 | To test if the quotation remains unchanged when Cancel Quotation is not clicked. | logged in,Url, Browser,Internet Active | Do not click Cancel Quotation. | Cancel Quotation: Not Clicked | Quotation should remain unchanged. | Quotation details remained unchanged when Cancel Quotation was not clicked. | Pass
Module 2 :- Sales Order Entry
Add more Item
Sc_08-tc01 | To test or verify that the mutiple items can be added or not in sales order entry . | logged in,Url, Browser,Internet Active ,New sales quotataion Entry should placed | 1.click on add item button 2: Select the item. 3: Increase the item quantity. | Item Code: 101 Item: iPad Air 2 16GB Quantity: 2 | Quantity should be increase successfully | Item quantity was increased successfully from 1 to 2. | Pass
Delete item
Sc_09 tc_01 | to test mutiple item get delete when click on delete button{refer sc_03}
sc_09 tc_02 | to test single item get delete when click on delete button{refer sc_03}
Edit item
Sc_10-tc01 | to test item get edit when quantity and discount are positive {refer sc_02}
Sc_10-tc02 | to test item get edit when quantity and discount are negative {refer sc_02}
Sc_10-tc_03 | to test item get edit when quantity is postive and discount is negative{refer sc_02}
Sc_10-tc_04 | to test iten get edit when discount is negative and quantity is positive {refer sc_02}
Place Order
Sc_11-tc_01 | to test quotation gets placed when current quotation date of "" valid until"" section in quotation delivery details is selected {refer to sc _06}
Sc_11-tc_02 | to test quotation gets placed when past quotation date of "" valid until"" section in quotation delivery details is selected{refer to sc_06}
Sc_11-tc_03 | to test quotation gets placed when future quotation date of "" valid until"" section in quotation delivery details is selected{refer to sc_06}
Sc_11-tc_04 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is valid{refer to sc_06}
Sc_11-tc_05 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is invalid{ refer to sc_06}
Sc_11-tc_06 | to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is blank{refer to sc_06}
Sc_11-tc_07 | to verify quotation gets placed when valid date such as persent and future date to place quotation{refer to sc_06}
Cancel Quotation
Sc_12-tc_01 | To test if the quotation is cancelled when Cancel Quotation is clicked and OK is selected{refer to sc_07}
Sc_12-tc_02 | To test if the quotation is cancelled when Cancel Quotation is clicked and Cancel is selected.{ refer to sc_07}
Sc_12-tc_03 | To test if the quotation remains unchanged when Cancel Quotation is not clicked.{refer to sc_07}
Back
Sc_13_tc01 | to test the when clicked on back navigate on perivous module{ refer to Sc_05}
Sc_13_tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged (refer to sc_05}
Module-3 :- Deliver Items for a Sales Order
Delivery from
Sc_14-tc01 | To test or verify user can select valid Delivery from section when click by the user | logged in,Url, Browser,Internet Active ,order should be placed. | 1.click on delivery from box 2.select the delivery from | eg. - Bandra kurla complex Godown --> | Application should be display correct item | Application should display selected Item Cotrrectly | Pass
Shipping Company List
Sc_15-tc_01 | To test or verify that the Shipping Company list is displayed Valid when accessed by the user. | logged in,Url, Browser,Internet Active ,order should be placed. | 1.click on Shipping Company 2.select the Shipping Company | eg. - the great easthern shipping company --> | Application should be display correct shipping company list | Same as expected result | Pass
This Delivery
Sc_16-tc01 | 1. To test or verify This Delivery gets updated when a valid order value is entered | Login, URL, Browser, Internet active,order should be placed | 1.Click on this This Delivery 2.The "" this Delivery "" value should be matched as same as ordered value | this Delivery value =1 --> | Application should be process sucessfully | Same as expected result | Pass
Sc_16-tc02 | 2. To test or verify This Delivery when an invalid/blank/negative value is entered. | Login, URL, Browser, Internet active,order should be placed | 1.Click on this This Delivery 2.The "" this Delivery "" value should be invalid/ blank | this delivery value =!@#$ | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on sales order. | Pass
Sc_16-tc03 | 3. To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Automatically put balance on back order”. | Login, URL, Browser, Internet active,order should be placed | 1.click on this Delivery 2.Add more than or less than value 3. Automatically put back order | this delivery value =12 | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on sales order. | Pass
Sc_16-tc04 | 4To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Cancel any quantities not delivered”. | Login, URL, Browser, Internet active,order should be placed | 1click on this Delivery 2.Add more than or less than value 3.cancel any quantites not delivered | this delivery value =-234 cancel any quantites not delivered | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on sales order. | Pass
Date
Sc_17-tc01 | To test or verify Deliver Items for a Sales Order date is future date | Login, URL, Browser, Internet active,order should be placed | 1. click on date button 2. select the future date | 25/10/2026 --> | Application should be display error messge "" date is incorrect"" | Application should display The entered date is out of fiscal year or is closed for further data entry. | Pass
Sc_17-tc02 | To test or verify Deliver Items for a Sales Order date is past date or default value | Login, URL, Browser, Internet active,order should be placed | 1. click on date button 2. select the past date | 25/09/2026 or 06/10/2026 --> | Application should be processed successfully | same as expected result | Pass
process dispatch Button
Sc_18-tc01 | To test or verify the process dispatch when valid Data are entered. | Login, URL, Browser, Internet active,order should be placed | 1.click on process dispatch button 2.enter the valid value | --> | Application should be process successfully | Same as expected result | Pass
Sc_18-tc02 | To test or verify the process dispatch when lnvalid/Blank Data are entered. | Login, URL, Browser, Internet active,order should be placed | 1.click on process dispatch button 2.enter the invalid/ blank value | --> | Application should be display error message "" enter a valid data"" | Application should display The entered date is out of fiscal year or is closed for further data entry. | Pass
Back button
Sc_19-tc_01 | to test the when clicked on back navigate on perivous module{ refer to Sc_05}
Sc_19-tc_02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged { refer to Sc_05}
update button
Sc_20-tc01 | to test item get updated when total amount calculate and shipping charge is invalid {refer to sc_04}
to test item get updated when total amount calculate and shipping charge is valid {refer to sc_04}
to test item get updated when total amount calculate and shipping charge is blank{refern to sc_04}
Clear quantity & reset Quantity button
Sc_21-tc01 | To test Clear Quantity sets This Delivery quantity to 0 and sets Total, Sub-total, Included Tax and Amount Total to 0. | Logged in, browser active, valid Sales Order with delivery item | 1. go to deliver items for a sales 2. click on clear quantity | Ordered Qty: 10 This Delivery: 10 --> | This Delivery quantity should become 0. Total = 0 Sub-total = 0 Included Tax = 0 Amount Total = 0 | This Delivery was cleared to 0; the total, sub-total, included tax and amount total were reset to 0. | Pass
Sc_21-tc02 | To test Reset Quantity sets This Delivery quantity equal to Ordered quantity and recalculates Total, Sub-total, Included Tax and Amount Total accordingly. | Logged in, browser active, valid Sales Order with delivery item | 1. go to deliver items for a sales 2. click on reset quantity | Ordered Qty: 10 This Delivery: 10 --> | his Delivery quantity should become equal to Ordered Quantity (10). Total, Sub-total, Included Tax and Amount Total should be recalculated correctly. | After clearing the quantity, the button label changed from Clear Quantity to Reset Quantity. | Fail
Sc_21_tc_03 | To test the Clear Quantity button is renamed to Reset Quantity after clearing the delivery quantity. | Logged in, browser active, valid Sales Order with delivery item | 1 Click Clear Quantity 2.button name changes Reset Quantity. | This Delivery: 5 --> | This Delivery quantity should become 0 and the Clear Quantity button should be renamed to Reset Quantity | Same as expected result | Pass
Module 4- : - Issue an Invoice for Delivery Note
Process invoice- to verify process invoice functionality
Sc_22-tc01 | test or verify that the Invoice Date is populated with the current/system date, allows a past date, and does not allow a future date. | 1. User is logged in to the application. 2. Valid delivery/invoice details are available for processing. 3. Required customer and item details are available. 4. User is on the Process Invoice screen. | 1.Navigate to the process invoice screen and verfiy the Invoice date field. 2. Check the default value invoice date is populated by the system. 3.Enter / select the past date in the invoice Date field . 4.Enter / select the future date in the invoice Date field | Current Date :- 06/10/2026 Past Date :- 05/10/2026 Future Date :- 10/10/2026 | 1. Invoice Date should show the current / system date by default . 2. The user should be able select a past date . 3.The user should not able to select a future date | The Invoice Date is populated with the current/system date by default. The user can select a past date, and a future date is not allowed | Fail
Sc_22-tc02 | To test or verify that the user can select the required Payment Terms from the available options. | 1. User is logged in. 2. User has access to the Process Invoice screen. 3. A valid invoice is available for processing. | 01: Navigate to the Process Invoice screen and click on the Payment Terms field. 02: Verify the available Payment Terms options. 03: Select the required Payment Terms from the available options | Payment Terms: Net 30 Days | 1. Available Payment Terms options should be displayed. 2. User should be able to select Net 30 Days. 3. The selected Payment Terms should be displayed correctly in the Payment Terms field. | The available Payment Terms options are displayed. The user can select Net 30 Days, and the selected option is displayed in the Payment Terms field. | Pass
Sc_22-tc03 | .To test or verify that the Due Date is calculated correctly based on the selected Payment Terms and Invoice Date. | 1. User is logged in. 2. User has access to the Process Invoice screen. 3. A valid invoice is available for processing. | 01: Navigate to Process Invoice screen and verify Invoice Date. 02: Select Payment due within 10 days from Payment Terms. 03: Verify the Due Date calculated by the system. | Invoice Date: 10/10/2026 Payment Terms: Payment due within 10 days Expected Due Date: 20/10/2026 | Due Date should be calculated correctly based on the selected Payment Terms and Invoice Date. For Invoice Date 10/10/2026 with Payment due within 10 days, Due Date should be 20/10/2026. | For Invoice Date 10/10/2026 and Payment Terms Payment due within 10 days, the system calculates the Due Date as 20/10/2026. | Pass
Sc_22-tc04 | test or verify that clicking Process Invoice successfully processes the invoice and creates the required dispatch entry | 1. User is logged in. 2. Process Invoice screen is accessible. 3. A valid delivery note is available for invoicing. | 01: Open the Process Invoice screen. 02: Verify the invoice details and the quantity available for invoicing 03: Click Process Invoice. | This Invoice: Quantity available for invoicing as per the Delivery Note | Invoice should be processed successfully and a dispatch entry should be created for the warehouse. | After clicking Process Invoice, the invoice is processed and the required dispatch entry is created for the warehouse. | Pass
to verify the Reference functionality
Sc_23-tc01 | To test or verify that the Reference is displayed for the invoice. | 1. User is logged in. 2. Process Invoice screen is accessible. 3. A valid Delivery Note is available for invoicing. | 01: Open the Process Invoice screen. 02: Check the Reference field. | Reference: System-generated value | Reference should be automatically generated and displayed for the invoice. | The Reference is automatically generated and displayed in the Reference field for the invoice | Pass
Sc_23-tc02 | To test or verify that the Reference is automatically generated for the invoice | 1. User is logged in. 2. Process Invoice screen is accessible. 3. A valid Delivery Note is available for invoicing. | 01: Open the Process Invoice screen. 02: Check the Reference field. | Reference: System-generated value | Reference should be automatically generated and displayed for the invoice. | The Reference is automatically generated for the invoice and displayed in the Reference field. | Pass
Back
Sc_24-tc01 | to test the when clicked on back navigate on perivous module{refer to sc_05}
Sc_24-tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged {refer to sc_05}
update
Sc_25-tc01 | to test item get updated when total amount calculate and shipping charge is invalid {refer to sc_04}
Sc_25-tc02 | to test item get updated when total amount calculate and shipping charge is valid {refer to sc_04}
Sc_25-tc03 | to test item get updated when total amount calculate and shipping charge is blank{refer to sc_04}
Module 5 :- Customer Payment Entry: Field Description
Date of Deposit
Sc_26-tc01 | To test or verify that Date of Deposit is populated with the system date by default. | Login, URL, Browser, Internet active. Customer Payment Entry screen is open. | 01: Open the Customer Payment Entry screen. 02: Check the Date of Deposit field. | Date of Deposit: Current system date | Date of Deposit field should be populated with the current system date by default. | The Date of Deposit field is populated with the current system date by default. | Pass
Sc_26-tc02 | To test or verify that Date of Deposit represents the date on which payment was deposited. | Customer Payment Entry screen is open. | 01: Open the Customer Payment Entry screen. 02: Check the Date of Deposit field. 03: Verify that the displayed date represents the date on which the payment was deposited. | Date of Deposit: Payment deposit date | Date of Deposit should represent the date on which the payment was deposited. | Date of Deposit field displays the date on which the payment was deposited. | Pass
Sc_26-tc_03 | To test or verify that Date of Deposit can be changed from the default system date to the payment deposit date. | Customer Payment Entry screen is open. | 01. Open the Customer Payment Entry screen. 02: Enter/select the date on which the payment was deposited in the Date of Deposit field. 03: Verify the Date of Deposit field. | Date of Deposit: Actual payment deposit date | Date of Deposit should display the date on which the payment was deposited. | The user can change the default system date and enter/select the actual payment deposit date. The selected date is displayed in the Date of Deposit field. | Pass
Bank Charge
Sc_27-tc_01 | To test or verify that Bank Charge can be entered when charges are levied by the bank. | Customer Payment Entry screen is open. | 01: Open the Customer Payment Entry screen. 02: Enter the bank charge in the Bank Charge field. 03: Verify the Bank Charge field. | Bank Charge: Bank charge applicable to the transaction | The entered bank charge should be displayed in the Bank Charge field | The entered bank charge is displayed in the Bank Charge field. | Pass
Sc_27-tc_02 | To test or verify that the entered Bank Charge is mentioned in the Bank Charge field. | Customer Payment Entry screen is open. | 01: Open the Customer Payment Entry screen. 02: Enter the applicable bank charge in the Bank Charge field. 03: Verify the Bank Charge field. | Bank Charge: Applicable bank charge | The entered bank charge should be displayed in the Bank Charge field. | The applicable bank charge is entered and displayed in the Bank Charge field | Pass
Sc_27-tc_03 | o test or verify that Bank Charge is captured for the payment transaction. | Customer Payment Entry screen is open with invoice amount available. | 01: Open the Customer Payment Entry screen. 02: Enter the discount amount in the Amount of Discount field. 03: Verify the Amount field. | Amount of Discount: Discount amount offered to the customer | Amount should display the final amount after deduction of the discount amount | The entered Bank Charge is captured for the payment transaction. | Pass
Amount of Discount
Sc_28-tc_01 | To test or verify that Amount of Discount can be entered when a discount is offered to the customer. | . Customer Payment Entry screen is open | 01: Open the Customer Payment Entry screen. 02: Enter the discount amount in the Amount of Discount field. 03: Verify the Amount of Discount field. | Amount of Discount: Discount amount offered to the customer | The entered discount amount should be displayed in the Amount of Discount field. | The entered discount amount is displayed in the Amount of Discount field. | Pass
Sc_28-tc_02 | To test or verify that the entered Amount of Discount is considered for the payment amount. | Customer Payment Entry screen is open with invoice amount available | 01: Open the Customer Payment Entry screen. 02: Enter the discount amount in the Amount of Discount field. 03: Verify the Amount field after entering the discount | Amount of Discount: Discount amount offered to the customer | The Amount should reflect the amount after considering the entered discount. | The Amount field reflects the payment amount after considering the entered discount. | Pass
Sc_28-tc_03 | 3 .To test or verify that Amount displays the final amount after deduction of the discount amount. | Customer Payment Entry screen is open with invoice amount available. | 01: Open the Customer Payment Entry screen. 02: Enter the discount amount in the Amount of Discount field. 03: Verify the Amount field. | Amount of Discount: Discount amount offered to the customer | Amount should display the final amount after deduction of the discount amount. | The Amount field displays the final amount after deducting the discount amount. | Pass
Amount
Sc_29-tc_01 | To test or verify that Amount displays the amount as per the invoice. | Customer Payment Entry screen is open with invoice details available. | 01: Open the Customer Payment Entry screen. 02: Check the Amount field against the invoice. 03: Verify the displayed amount | Invoice Amount: Amount as per the raised invoice | Amount field should display the amount as per the invoice. | The Amount field displays the amount as per the raised invoice | Pass
Sc_29-tc_02 | to test or verify that Amount displays the final amount after deduction of the discount amount. | Customer Payment Entry screen is open with invoice amount and discount details available. | 01: Open the Customer Payment Entry screen. 02: Enter the discount amount in the Amount of Discount field. 03: Verify the Amount field | Amount of Discount: Discount amount offered to the customer | Amount field should display the final amount after deduction of the discount amount | The Amount field displays the final amount after deducting the discount amount entered in the Amount of Discount field. | Pass
Add Payment
Sc_30-tc_01 | to test or verify that Add Payment button is available to submit the customer payment. | Customer Payment Entry screen is open. | 01: Open the Customer Payment Entry screen. 02: Check the Add Payment button. | Payment Entry: Customer payment details entered | Add Payment button should be available to submit the customer payment | The Add Payment button is available on the Customer Payment Entry screen | Pass
Sc_30-tc_02 | To test or verify that clicking Add Payment makes a successful Payment Entry to the customer. | Customer Payment Entry details are entered. | 01: Enter the required customer payment details. 02: Click the Add Payment button. 03: Verify the payment entry. | Customer Payment Details: Entered payment details | Clicking Add Payment should make a successful Payment Entry to the customer. | After clicking Add Payment, the customer payment entry is created successfully. | Pass
Sc_30-tc_03 | To test or verify that the entered payment details are submitted through Add Payment. | Customer Payment Entry details are entered. | 01: Enter the customer payment details. 02: Click the Add Payment button. 03: Verify that the entered payment details are submitted. | Payment Details: Entered customer payment details | The entered payment details should be submitted through Add Payment. | The entered customer payment details are submitted through the Add Payment button. | Pass
Reference
Sc_31-tc_01 | To test or verify that the Reference is displayed for the invoice.{refer to Sc_23}
Sc_31-tc_02 | To test or verify that the Reference is automatically generated for the invoice{reder to sc_23}
Back
Sc_32-tc_01 | to test the when clicked on back navigate on perivous module{refer to sc_05}
Sc_32-tc_02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged {refer to sc_05}
Section 2
Module 6 - Purchase Order Entry
Supplier & Receive Into
Sc_33-tc01 | To test or verify user can select required Valid section when value is correctly dropdown | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Drop down arrow 2.Select Approriate Value 3.Click on value | eg. Dino --> | Application should display selected Item Correctly | Same as Expected Result | Pass
Supplier's Reference
Sc_34-tc01 | To test or verify that the user can enter Valid alphanumeric Reference value | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Supplier’s Reference 2.Enter alphanumeric value | abc787x | Reference Number gets add successfully | Reference Number gets add successfully | Pass
Sc_34-tc02 | To test or verify that the user can enter Blank Reference value | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Supplier’s Reference 2.Enter alphanumeric value | ' '' | Application should display Error Message | Application Doesn't show Error Message | fail
Deliver to
Sc_35-tc01 | To test or verify user enter valid address | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Deliver to field 2.Enter Address | Near Shamsheer Non-veg restuarant | Address gets add successfully | Same as Expected Result | Pass
Sc_35-tc02 | To test or verify user enter Invalid address | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Deliver to field 2.Enter Address | N/A | Application should display Error Message | Application Doesn't show Error Message | fail
Sc_35-tc03 | To test or verify user enter Blank address | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Deliver to field 2.Enter Address | "" """ | Application should display Error Message | Application should display There is no delivery address specified. | Pass
Add item
Sc_36-tc01 | To test item get add when Item code is enterned negative and quantity,price,required delivery date are are positive | URL and Intetrnet Active, Browser Working, Register user | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item | -22222 iPad Air 2 16GB 1 300 10/20/2026 --> | Item should not add and shows error message"" "Invalid Item Code or Description Entered"" | Application Doesn't show Error Message | Fail
Sc_36-tc02 | To test item get add when quantity is enterned negative and add code,price,required delivery date are are positive | URL and Intetrnet Active, Browser Working, Register user | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item | 101 iPad Air 2 16GB 21 !@#$%^ 300 10/20/2026 --> | Item should not add and shows error message""The quantity of the order item must be numeric and not less than 1"" | Application should display Error Message "The item could not be updated because you are attempting to set the quantity ordered to less than 0 | Pass
Sc_36-tc03 | To test item get add when price is enterned negative and add code,quantity,required delivery date are are positive | URL and Intetrnet Active, Browser Working, Register user | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item | 101 iPad Air 2 16GB 21 1 !@#$%^ 10/20/2026 --> | price should be not added it's show the actual price item"" Its shows the default value"" | "Application should display Error Message ""Price 0.00 is below Standard Cost 297.35""" | Pass
Sc_36-tc04 | To test item get add when required delivery date is enterned negative and add code,quantity,price are are positive | URL and Intetrnet Active, Browser Working, Register user | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item | 101 iPad Air 2 16GB 21 1 300 !@#$%^ --> | date is not valid shows error message ""The date entered is in an invalid format."" | Same as expected result | Pass
Sc_36-tc05 | To test item get add when item code,quantity ,price ,required delivery date is positive | URL and Intetrnet Active, Browser Working, Register user | 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item | 2 iPad Air 2 16GB 1 300 10/20/2026 --> | Order Items should be add successfully | Same as expected result | pass
Edit Item
Sc_37 -tc01 | to test item get edit when quantity and required delivery date are positive | URL and Intetrnet Active, Browser Working, Register user ,add item | 1.Enter to Add item 2.clcik on edit button 3. enter a quantity 4. enter a required delivery date --> | 1 10/20/2026 --> | Item should be edit successfully | Same as expected result | pass
Sc_37-tc02 | to test item get edit when quantity and required delivery date are negative | URL and Intetrnet Active, Browser Working, Register user ,add item | 1.Enter to Add item 2.clcik on edit button 3. enter a quantity 4. enter a required delivery date --> | -222222 !@#$%^ --> | item should be not edit shows error message | application should be display the error message ''The quantity of the order item must be numeric and not less than 1 "' | Pass
Sc_37-tc03 | to test iten get edit when quantity is negative and required delivery date is positive | URL and Intetrnet Active, Browser Working, Register user ,add item | 1.Enter to Add item 2.clcik on edit button 3. enter a quantity 4. enter a required delivery date --> | -222222 10/20/2026 --> | item should be not edit shows error message | application should be display the error message ''The quantity of the order item must be numeric and not less than 1 "' | Pass
Sc_37-tc04 | to test item get edit when quantity is postive and required delivery date is negative | URL and Intetrnet Active, Browser Working, Register user ,add item | 1.Enter to Add item 2.clcik on edit button 3. enter a quantity 4. enter a required delivery date --> | 2 !@#$%^ --> | item should be not edit shows error message | Application should be displayed error message""The date entered is in an invalid format."" | Pass
Delete item
Sc_38-tc01 | to test single item get delete when click on delete button | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.click on delete ""X bar icon"" | Order Items | Item should be delete successfully | same as expected result | Pass
Sc_38-tc02 | to test Mutiple item get delete when click on delete button | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.click on delete ""X bar icon"" | Order Items | item should be not delete multiple item | same as expected result | fail
Order Date
Sc_39-tc01 | To test or verify Purchase Order Entry date is future date | Login, URL, Browser, Internet active | 1.click on calendar bar 2. select a date | 09/25/2026 --> | Application should be display error messge "" date is incorrect"" | Application should show the error message | fail
Sc_39-tc02 | To test or verify Purchase Order Entry date is default date or past date | Login, URL, Browser, Internet active | 1.click on calendar bar 2. select a date | 25/09/2026 or 06/10/2026 --> | Application should be processed successfully | same as expected result | Pass
Place order button
Sc_40-tc01 | To test or verify the place order get placed when valid Data are entered. | Login, URL, Browser, Internet active | 1. click on place order button 2. Enter a valid data | --> | Application should be process successfully | same as expected result | Pass
Sc_40-tc02 | To test or verify the process for dispatching selected item when lnvalid/Blank Data are entered. | Login, URL, Browser, Internet active | 1. click on place order button 2.enter the invalid/ blank value | --> | Application should display "You must enter at least one non empty item line." | same as expected result | Pass
Cancel order
Sc_41-tc01 | To test or verify the Cancel order button should clear the page and displayed back | URL and Intetrnet Active, Browser Working, Register user | 1. click on cancel order botton 2. add item | --> | Application should be cancel order and navigate previous the module | same as expected result | Pass
Sc_41-tc02 | To test or verify the Cancel order button should not clear the page and not navigate back module | URL and Intetrnet Active, Browser Working, Register user | 1. click on cancel order botton 2. add item | --> | Application should be display the same page and not cancel the order | Application should display Message " You are about to void this Document, Do you want to continue" | pass
Back
Sc_42-tc01 | to test the when clicked on back navigate on perivous module | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.Click on "Back" Button | --> | Application should be navigate perivous page | same as expected result | Pass
Sc_42-tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged | logged in,Url, Browser,Internet Active ,user logged ,item added | 1.Click on "Back" Button | --> | Application should be same page not navigate the previous page | Application should display blank data | pass
Module 7 - Receive Purchase Order Items
update
Sc_43-tc01 | To test or verify can update This delivery data when Quantity is Equal Ordered unit | URL and Intetrnet Active, Browser Working, Register user | 1.Click on this Delivery 2.Enter This Delivery 3.Click on Update Button | 1 | Value gets add successfully | Value gets add successfully | Pass
Sc_43-tc02 | To test or verify can update This delivery data when Quantity is More then Ordered unit | URL and Intetrnet Active, Browser Working, Register user | 1.Click on this Delivery 2.Enter This Delivery 3.Click on Update Button | 100 | Application should display Error Message | "Application should display Entered quantities cannot be greater than the quantity entered on the purchase order including the allowed over-receive percentage (10%). Modify the ordered items on the purchase order if you wish to increase the quantities." | Pass
Sc_43-tc03 | To test or verify can update This delivery data when Quantity is Blank Ordered unit | URL and Intetrnet Active, Browser Working, Register user | 1.Click on this Delivery 2.Enter This Delivery 3.Click on Update Button | """" """" | Application should display Error Message | Application should display There is nothing to process. Please enter valid quantities greater than zero.. | Pass
Process Receive Item
Sc_44-tc01 | 1) To test or verify the Purchase get Processed when valid Data are entered | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Process Receive Item Button | --> | Application should process the Receive Purchase Order successfully | Same as Expected Result | Pass
Sc_44-tc02 | To test or verify the Purchase get Processed when Invalid Data are entered | URL and Intetrnet Active, Browser Working, Register user | Click on Process Receive Item Button | --> | Application should display Error Message | Application Doesn't show Error Message | Fail
Back
Sc_45-tc01 | to test the when clicked on back navigate on perivous module{ refer to sc_42}
Sc_45-tc01 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged{ refer to sc_42}
This Delivery
Sc_46-tc01 | 1. To test or verify This Delivery gets updated when a valid value is entered | Login, URL, Browser, Internet active,order should be placed | 1.Click on this This Delivery 2.The "" this Delivery "" value should be matched as same as ordered value | this Delivery value =1 --> | Application should be process sucessfully | Same as expected result | Pass
Sc_46-tc02 | 2. To test or verify This Delivery when an negative value is entered. | Login, URL, Browser, Internet active,order should be placed | 1.Click on this This Delivery 2.The "" this Delivery "" value should be invalid | this delivery value =!@#$ | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on purchase order. | Pass
Sc_46-tc03 | 3. To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Automatically put balance on back order”. | Login, URL, Browser, Internet active,order should be placed | 1.click on this Delivery 2.Add more than or less than value 3. Automatically put back order | this delivery value =12 | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on purchase order. | Pass
Sc_46-tc04 | 4To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Cancel any quantities not delivered”. | Login, URL, Browser, Internet active,order should be placed | 1click on this Delivery 2.Add more than or less than value 3.cancel any quantites not delivered | this delivery value =-234 cancel any quantites not delivered | Application should be display the error message | Application should display Selected quantity cannot be less than quantity invoiced nor more than quantity not dispatched on sales order. | Pass
Module 8 - Enter Supplier invoice
Quantity Items Received for invoice
Sc_47-tc01 | 1) To test or verify the user can enter "Qty Yet To Invoice" is equal or less than "Quantity Received" | URL and Intetrnet Active, Browser Working, Register user | 1.Click on "Qty Yet To Invoice" 2.Enter Value | 15 | Value gets add successfully | Same as expected result | Pass
Sc_47-tc02 | To test or verify the user can enter "Qty Yet To Invoice" is Blank "Quantity Received" | URL and Intetrnet Active, Browser Working, Register user | Click on "Qty Yet To Invoice" Enter Value | """ """" | Application should display Error Message | Application should display The invoice cannot be processed because the there are no items or values on the invoice. Invoices are expected to have a charge. | Pass
Sc_47-tc03 | To test or verify the user can enter "Qty Yet To Invoice" is Negative "Quantity Received" | URL and Intetrnet Active, Browser Working, Register user | Click on "Qty Yet To Invoice" Enter Value | -15 | Application should display Error Message | Application should display The invoice cannot be processed because the there are no items or values on the invoice. Invoices are expected to have a charge. | Pass
Enter Invoice button
Sc_48-tc01 | To test or verify the Purchase Invoice get Processed when valid Data are entered | URL and Intetrnet Active, Browser Working, Register user | Click on Enter Invoice button | --> | Application should process the Enter Supplier Invoice successfully | same as expected result | Pass
Sc_48-tc02 | To test or verify the Purchase Invoice get Processed when Invalid Data are entered | URL and Intetrnet Active, Browser Working, Register user | Click on Enter Invoice button | --> | Application should display Error Message | Application should display The invoice cannot be processed because the there are no items or values on the invoice. Invoices are expected to have a charge. | Pass
Add All Item
Sc_49-tc01 | To test or verify user can add all the Purchase items at once. | URL and Intetrnet Active, Browser Working, Register user | Click on Add All Items Button | --> | Items gets Add successfully | Same as expected result | Pass
Tax and Update Button
Sc_50-tc01 | To test or verify Total amount gets calculate correctly when user add valid Tax charge | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Tax Charge 2.Enter Tax Amount | 1050 ( 5% ) | Tax gets add successfully | Same as expected result | Pass
Sc_50-tc02 | To test or verify Total amount gets calculate correctly when user add Invalid Tax charge | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Tax Charge 2.Enter Tax Amount | "Abc@34#" ( 5% ) | Application should display Error Message | Application Doesn't show Error Message | Fail
Supplier's Reference
Sc_51-tc01 | To test or verify that the user can enter Valid alphanumeric Reference value { refer to sc_34}
Sc_51-tc02 | To test or verify that the user can enter Blank Reference value Turn on screen reader support{ refer to sc_34}
update
Sc_52-tc01 | To test or verify can update This delivery data when Quantity is Equal Ordered unit{refer to Sc_43}
Sc_52-tc02 | To test or verify can update This delivery data when Quantity is More then Ordered unit{refer to sc_43}
Sc_52-tc03 | To test or verify can update This delivery data when Quantity is Blank Ordered unit{refer to sc_43}
Back
Sc_53-tc01 | to test the when clicked on back navigate on perivous module{refer to sc_42}
Sc_53-tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged{refer to sc_42}
Module 9 - Supplier Payment Entry
Bank Amount
Sc_54-tc01 | Test or verify user can enter Valid Bank amount when select retailer | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Bank Charges 2.Enter Bank Charges Amount | 100 | Amount gets add successfully | Same as expected result | Pass
Sc_54-tc02 | Test or verify user can enter Invalid Bank amount when Customer is Retailer | URL and Intetrnet Active, Browser Working, Register user | Click on Bank Charges Enter Bank Charges Amount | Abc@34# | Application should display Error Message | Application Doesn't show Error Message | Fail
This Allocation
Sc_55-tc01 | 1) To test or verify This allocation display correctly when user click on All link the total amount of field will be show | URL and Intetrnet Active, Browser Working, Register user | Click on "All" Button | --> | all Amount gets add successfully | Same as Expected Result | Pass
Sc_55-tc02 | To test or verify This allocation feild when user enter Negative values | URL and Intetrnet Active, Browser Working, Register user | Click on "All" Button Enter Amount in This Allocation | --> | Application should display Error Message Invalid Amount | Application should display The total of the amount and the discount is zero or negative. Please enter positive values. | Pass
Sc_55-tc03 | To test or verify This allocation feild when user enter Blank values | URL and Intetrnet Active, Browser Working, Register user | 1.Click on "All" Button 2.Enter Amount in This Allocation | --> | Application should display Error Message Invalid Amount | Application should display The total of the amount and the discount is zero or negative. Please enter positive values. | Pass
None
Sc_56-tc01 | 1) To test or verify This allocation field gets Blank when user click on None Button | URL and Intetrnet Active, Browser Working, Register user | Click on "None" Button | --> | Application should display all field gets blank | Same as expected result | Pass
Amount of Discount
Sc_57-tc01 | 1) To test or verify user can add discount in "Amount of Discount" when valid value will be enter | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Amount of Discount 2.Enter Discount Amount | 100 | Discount gets add successfully | Same as Expected Result | Pass
Sc_57-tc02 | To test or verify user can add discount in "Amount of Discount" when Invalid value will be enter | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Amount of Discount 2.Enter Discount Amount | Abc@34# | Application should display Error Message | Application should display The total of the amount and the discount is zero or negative. Please enter positive values. | Pass
Amount of Payment
Sc_58-tc01 | To test or verify user can add or enter valid Payment amount value | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Amount of Payment 2.Enter Amount which should be paid | $5000 | all Amount gets add successfully | Same as expected result | Pass
Sc_58-tc02 | To test or verify user can add or enter Invalid Payment amount value | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Amount of Payment 2.Enter Amount which should be paid | Abc@34# $ | Application should display Error Message Invalid Amount | Application should display The total of the amount and the discount is zero or negative. Please enter positive values. | Pass
Enter a Payment Button
Sc_59-tc01 | To test or verify the Payment get placed when valid Payment Amount, Bank charges,This allocation , Amount and Discount are entered. | URL and Intetrnet Active, Browser Working, Register user | 1.Click on "Enter Payment" Button | --> | Application should process the Supplier Payment Entry successfully | Same as expected result | Pass
Sc_59-tc02 | To test or verify the Payment get placed when Invalid Payment Amount, Bank charges,This allocation , Amount and Discount are entered. | URL and Intetrnet Active, Browser Working, Register user | Click on "Enter Payment" Button | --> | Application should display Error Message Invalid Data or Input enter | The total of the amount and the discount is zero or negative. Please enter positive values. | Pass
Section 3
Module 10- Inventory Location Transfers: Field Description
Date
Sc_60-tc01 | To test or verify date is accepted when Past date and present date should be selected | URL and Intetrnet Active, Browser Working, Register user | 1".Click on Date 2.Seletct Date" | 05-12-2026 10-14-2026 | Date should gets add successfully | Date should gets add successfully | Pass
Sc_60-tc02 | To test or verify date is accepted when Future date should be selected | URL and Intetrnet Active, Browser Working, Register user | 1.Click on Date 2. Seletct Date | 2026-12-12 | Application should display The entered date incorrect | Application should display The entered date is out of fiscal year or is closed for further data entry. | Pass
From Location & To Location
Sc_61-tc01 | To test or verify user can select differenet selection for From location & To location data | URL and Intetrnet Active, Browser Working, Register user | 1.Select From Location 2.Select To Location | Bandra Kurla Complex Godown Thane - Station Warehouse | Address should gets add successfully | Same as Expected Result | Pass
Sc_61-tc02 | To test or verify user can select same selection for From location & To location data | URL and Intetrnet Active, Browser Working, Register user | 1.Select From Location 2.Select To Location | Bandra Kurla Complex Godown Bandra Kurla Complex Godown | Application should display wrong or same location selected | Application should display The locations to transfer from and to must be different.. | Pass
Items
Sc_62-tc01 | To test or verify Item gets add when Item code, Item Description, Quantity entered valid | URL and Intetrnet Active, Browser Working, Register user | 1.Enter Item Code 2.Select Item Description 3.Enter Quantity | 103 iPhone Cover Case 100 | Date should gets add successfully | Same as Expected Result | Pass
Sc_62-tc02 | To test or verify Item gets add when Item code is kept Invalid and Item Description, Quantity entered valid | URL and Intetrnet Active, Browser Working, Register user | 1.Enter Item Code 2.Select Item Description 3.Enter Quantity | 1003 iPhone Cover Case 100 | Application should display Error Message "Invalid Item Code or Description Entered" | Application Doesn't show Error Message | Fail
Sc_62-tc03 | To test or verify Item gets add when Item Description is kept Invalid and Item code, Quantity entered valid | URL and Intetrnet Active, Browser Working, Register user | 1.Enter Item Code 2.Select Item Description 3. Enter Quantity | 103 Support 100 | Application should display Error Message "Invalid Item Code or Description Entered" | Application should display Error Message "For Part :103 This item is already on this document. You can change the quantity on the existing line if necessary." | Pass
Sc_62-tc04 | To test or verify Item gets add when Quantity is kept Invalid and Item code, Item Description entered valid | URL and Intetrnet Active, Browser Working, Register user | 1.Enter Item Code 2.Select Item Description 3. Enter Quantity | 103 iPhone Cover Case Abc@34# | Application should display Error Message "Invalid Quantity Entered" | Application should display Error Message "The quantity entered must be a positive number." | Pass
Process Transfer
Sc_63-tc01 | To test or verify the Process Transfer get Processed when valid Data are entered | URL and Intetrnet Active, Browser Working, Register user | 1.Click on 2.Process Transfer Button | --> | Application should process the Inventory Location Transfers successfully | Application should process the Inventory Location Transfers successfully | Pass
Sc_63-tc02 | To test or verify the Process Transfer get Processed when Invalid Data are entered | URL and Intetrnet Active, Browser Working, Register user | 1.Click on 2. Process Transfer Button" | --> | Application should display Error Message Invalid Data or Input enter | Application should display Error Message "You must enter at least one non empty item line." | Pass
Back
Sc_64-tc01 | to test the when clicked on back navigate on perivous module | URL and Intetrnet Active, Browser Working, Register user | 1.Click on "Back" Button | --> | Application should be navigate perivous page | Same as expected result | Pass
Sc_64-tc02 | To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged | URL and Intetrnet Active, Browser Working, Register user | 1.Click on "Back" Button | --> | Application should be same page not navigate the previous page | Application should display blank data | Pass

## Bug Report
Defect ID | Date | Project Name | Module Name | Sub- Module Name | Version | Phase | Type | summary | Descriptoion | Severity | Priority | Reported by | Reported to | status
DF-01 | 2026-10-20 | front Accounting | sales quotation entry | add item | 2.4.15 | System phase | Functional defect - missing | Accepts negative value in quantity | "1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Discount 6..enter a Add item Quantity should be not added and shows Default value""Quantity shows the 0 value "Application should display Error Message ""The item could not be updated because you are attempting to set the quantity ordered to less than 0, or the discount percent to more than 100.""" | low |  | Devesh pandey | Rajini Ma'am | new
DF-02 | 2026-10-21 | Front Accounting | sales quotation entry | Delete item | 2.4.15 | System phase | Functional defect - missing | Multiple items are deleted when clicking the Delete (X) icon | 1.click on delete ""X bar icon"" item should be not delete multiple item same as expected result | Low |  | Devesh pandey | Rajini Ma'am | New
DF-03 | 2026-10-21 | Front Accounting | sales quotation entry | update item | 2.4.15 | System phase | Functional defect -missing | Application does not display an error message for invalid shipping charges | "1. click on update button 2.total amount calculated 3Enter a shipping charge 4.Enter a update button item should be not update show ""error message"" Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-04 | 2026-10-21 | Front Accounting | sales quotation entry | update item | 2.4.15 | System phase | Functional defect - missing | Application does not update the item when shipping charges are left blank | "1. click on update button 2.total amount calculated 3Enter a shipping charge 4.Enter a update button" item should be update successfully Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-05 | 2026-10-21 | Front Accounting | sales quotation entry | Place order Button | 2.4.15 | System phase | Functional Defect-missing | Application does not display a validation message for the selected Valid Until date | "1. select a Quotation Delivery details 2. click on Calender icon button 3.Select Valid Until Date" Error/validation message should be displayed for the future quotation date and quotation should not be placed. Application Doesn't show Error Message | Medium |  | Devesh pandey | Rajini Ma'am | New
DF-06 | 2026-10-21 | Front Accounting | sales quotation entry | Place order Button | 2.4.15 | System phase | Functional Defect-missing | Application does not display validation messages when mandatory delivery details are blank | "1. select a Quotation Delivery detail 2.Enter valid Deliver To, Address, and Contact Number" "Application should display ""You must enter the person or company to whom delivery should be made to"" “You should enter the street address in the box provided. Orders cannot be accepted without a valid street address. ""contact number must be a valid 10-digit number""" Application Doesn't show Error Message | Medium |  | Devesh pandey | Rajini Ma'am | New
DF-07 | 2026-10-21 | Front Accounting | Deliver Items for a Sales Order | Clear quantity & reset Quantity button | 2.4.15 | System phase | Functional Defect-missing | Reset Quantity button label changes unexpectedly after clearing the quantity | "1. go to deliver items for a sales 2. click on reset quantity " "his Delivery quantity should become equal to Ordered Quantity (10). Total, Sub-total, Included Tax and Amount Total should be recalculated correctly." After clearing the quantity, the button label changed from Clear Quantity to Reset Quantity. | Low |  | Devesh pandey | Rajini Ma'am | New
DF_08 | 2026-10-21 | Front Accounting | Issue an Invoice for Delivery Note | Process invoice- to verify process invoice functionality | 2.4.15 | System phase | Functional Defect-missing | Invoice Date validation test case fails | "1.Navigate to the process invoice screen and verfiy the Invoice date field. 2. Check the default value invoice date is populated by the system. 3.Enter / select the past date in the invoice Date field . 4.Enter / select the future date in the invoice Date field " "1. Invoice Date should show the current / system date by default . 2. The user should be able select a past date . 3.The user should not able to select a future date" The Invoice Date is populated with the current/system date by default. The user can select a past date, and a future date is not allowed | Low |  | Devesh pandey | Rajini Ma'am | New
DF-09 | 2026-10-21 | Front Accounting | Purchase Order Entry | Supplier's Reference | 2.4.15 | System phase | Functional defect - missing | Application should display Error Message | "1.Click on Supplier’s Reference 2.Enter alphanumeric value" Application should display Error Message Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-10 | 2026-10-21 | Front Accounting | Purchase Order Entry | Deliver to | 2.4.15 | System phase | Functional Defect-missing | Application should display Error Message | "1.Click on Deliver to field 2.Enter Address" Application should display Error Message Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-11 | 2026-10-21 | Front Accounting | Purchase Order Entry | Add item | 2.4.15 | System phase | Functional Defect-missing | Accepts negative value in quantity | " 1.Enter a Item code 2.Select a Item Description 3.Enter a Quantity 4. Enter a Price after Tax 5. Required delivery date 6..enter a Add item " Item should not add and shows error message"" "Invalid Item Code or Description Entered"" Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-12 | 2026-10-21 | Front Accounting | Purchase Order Entry | Delete item | 2.4.15 | System phase | Functional Defect-missing | Multiple items are deleted when clicking the Delete (X) icon | 1.click on delete ""X bar icon"" item should be not delete multiple item same as expected result | Low |  | Devesh pandey | Rajini Ma'am | New
DF-13 | 2026-10-21 | Front Accounting | Purchase Order Entry | Order Date | 2.4.15 | System phase | Functional Defect-missing | Application does not display an error message for an invalid purchase order date | "1.click on calendar bar 2. select a date " Application should be display error messge "" date is incorrect"" Application should show the error message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-14 | 2026-10-21 | Front Accounting | Purchase Order Entry | Process Receive Item | 2.4.15 | System phase | Functional Defect-missing | Application should display Error Message | Click on Process Receive Item Button Application should display Error Message Application Doesn't show Error Message | Medium |  | Devesh pandey | Rajini Ma'am | New
DF-15 | 2026-10-21 | Front Accounting | Enter Supplier invoice | Tax and Update Button |  | System phase | Functional defect - missing | Application should display Error Message | "1.Click on Tax Charge 2.Enter Tax Amount" Application should display Error Message Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-16 | 2026-10-21 | Front Accounting | Supplier Payment Entry | Bank Amount |  | System phase | Functional defect -missing | Application should display Error Message | "Click on Bank Charges Enter Bank Charges Amount" Application should display Error Message Application Doesn't show Error Message | Low |  | Devesh pandey | Rajini Ma'am | New
DF-17 | 2026-10-21 | Front Accounting | Inventory Location Transfers: Field Description | Items |  | System phase | Functional Defect-missing | Application should display Error Message "Invalid Item Code or Description Entered" | "1.Enter Item Code 2.Select Item Description 3.Enter Quantity" Application should display Error Message "Invalid Item Code or Description Entered" "Application Doesn't show Error Message " | Low |  | Devesh pandey | Rajini Ma'am | New

## m1 Sc_01-tc_01 to Sc02-tc_04
Sc_01-tc_01 - To test item get add when Item code is enterned negative and quantity,price,dicsount are are positive
Add item
Sc_01-tc_02 - To test item get add when quantity is enterned negative and add code,price,dicsount are are positive
Sc_01-tc_03 - To test item get add when price is enterned negative and add code,quantity,dicsount are are positive
Sc_01-tc_04 - To test item get add when discount is enterned negative and add code,quantity,price are are positive
Sc_01-tc_05 - To test item get add when item code,quantity ,price ,discount is positive
Sc_02-tc_01 - to test item get edit when quantity and discount are positive
Edit item
Sc_02-tc_02 - to test item get edit when quantity and discount are negative
Sc_02-tc_03 - to test item get edit when quantity is postive and discount is negative
Sc_02-tc_04 - to test iten get edit when quantity is negative and discount is positive

## Sc_03-tc_01 to Sc_05-tc_02
Sc_03-tc_01 - to test single item get delete when click on delete button
delete item
Sc_03-tc_02 - to test mutiple item get delete when click on delete button
Sc_04-tc01 - to test item get updated when total amount calculate and shipping charge is invalid
updated items
Sc_04-tc02 - to test item get updated when total amount calculate and shipping charge is valid
Sc_04-tc03 - to test item get updated when total amount calculate and shipping charge is blank
Sc_05-tc01 - to test the when clicked on back navigate on perivous module
Back Button
Sc_05-tc02 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged

## Sc_06-tc_01 to Sc_07-tc_03
Sc_06-tc01 - to test quotation gets placed when current quotation date of "" valid until"" section in quotation delivery details is selected
Placed Quotation
Sc_06-tc02 - to test quotation gets placed when past quotation date of "" valid until"" section in quotation delivery details is selected
Sc_06-tc03 - to test quotation gets placed when future quotation date of "" valid until"" section in quotation delivery details is selected
Sc_06-tc04 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is valid
Sc_06-tc05 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is invalid
Sc_06-tc06 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is blank
Sc_06-tc07 - to verify quotation gets placed when valid date such as persent and future date to place quotation
Sc_07-tc01 - To test if the quotation is cancelled when Cancel Quotation is clicked and OK is selected
Cancel Quotation
Sc_07-tc02 - To test if the quotation is cancelled when Cancel Quotation is clicked and Cancel is selected.
Sc_07-tc03 - To test if the quotation remains unchanged when Cancel Quotation is not clicked.

## m2 Sc08-tc_01 to Sc_13-tc_02
Sc_08-tc01 - To test or verify that the mutiple items can be added or not in sales order entry .
Add more item
Delete item
Sc_09 tc_01 - to test mutiple item get delete when click on delete button{refer sc_03 - tc 01}
sc_09 tc_02 - to test single item get delete when click on delete button{refer sc_03 - tc_02}
Edit item
Sc_10-tc01 - to test item get edit when quantity and discount are positive {refer sc_02}
Sc_10-tc02 - to test item get edit when quantity and discount are negative {refer sc_02}
Sc_10-tc_03 - to test item get edit when quantity is postive and discount is negative{refer sc_02}
Sc_10-tc_04 - to test iten get edit when discount is negative and quantity is positive {refer sc_02}
placed Order
Sc_11-tc_01 - to test quotation gets placed when current quotation date of "" valid until"" section in quotation delivery details is selected {refer to sc _06}
Sc_11-tc_02 - to test quotation gets placed when past quotation date of "" valid until"" section in quotation delivery details is selected{refer to sc_06}
Sc_11-tc_03 - to test quotation gets placed when future quotation date of "" valid until"" section in quotation delivery details is selected{refer to sc_06}
Sc_11-tc_04 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is valid{refer to sc_06}
Sc_11-tc_05 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is invalid{ refer to sc_06}
Sc_11-tc_06 - to test quotation gets placed when delivery details of "" valid until"" section in quotation delivery details is blank{refer to sc_06}
Sc_11-tc_07 - to verify quotation gets placed when valid date such as persent and future date to place quotation{refer to sc_06}
Cancel Order
Sc_12-tc_01 - To test if the quotation is cancelled when Cancel Quotation is clicked and OK is selected{refer to sc_07}
Sc_12-tc_02 - To test if the quotation is cancelled when Cancel Quotation is clicked and Cancel is selected.{ refer to sc_07}
Sc_12-tc_03 - To test if the quotation remains unchanged when Cancel Quotation is not clicked.{refer to sc_07}
Back
Sc_13_tc01 - to test the when clicked on back navigate on perivous module{ refer to Sc_05}
Sc_13_tc02 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged (refer to sc_05}

## m3 sc_14 -tc01 to sc_21-tc03
Sc_14-tc01 - To test or verify user can select valid Delivery from section when click by the user
Delivery from
Shipping Company List
Sc_15-tc_01 - To test or verify that the Shipping Company list is displayed Valid when accessed by the user.
This Delivery
Sc_16-tc01 - 1. To test or verify This Delivery gets updated when a valid order value is entered
Sc_16-tc02 - To test or verify This Delivery when an invalid/blank/negative value is entered.
Sc_16-tc03 - 3. To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Automatically put balance on back order”.
Sc_16-tc04 - 4To test or verify This Delivery when dispatching quantity is less than/more than ordered quantity and action for balance is “Cancel any quantities not delivered”.
DATE
Sc_17-tc01 - To test or verify Deliver Items for a Sales Order date is future date
Sc_17-tc02 - To test or verify Deliver Items for a Sales Order date is past date or default value
process dispatch Button
Sc_18-tc01 - To test or verify the process dispatch when valid Data are entered.
Sc_18-tc02 - To test or verify the process dispatch when lnvalid/Blank Data are entered.
Clear quantity & reset Quantity button
Sc_21-tc01 - To test Clear Quantity sets This Delivery quantity to 0 and sets Total, Sub-total, Included Tax and Amount Total to 0.
Sc_21-tc02 - To test Reset Quantity sets This Delivery quantity equal to Ordered quantity and recalculates Total, Sub-total, Included Tax and Amount Total accordingly.
Sc_21_tc_03 - To test the Clear Quantity button is renamed to Reset Quantity after clearing the delivery quantity.
Back
Sc_19-tc_01 - to test the when clicked on back navigate on perivous module{refer to sc_05}
Sc_19-tc02 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged {refer to sc_05}
update
Sc_20-tc01 - to test item get updated when total amount calculate and shipping charge is invalid {refer to sc_04}
Sc_20-tc02 - to test item get updated when total amount calculate and shipping charge is valid {refer to sc_04}
Sc_20-tc03 - to test item get updated when total amount calculate and shipping charge is blank{refern to sc_04}

## m4 & m5 sc_22-tc01 to sc_32-tc0
Process invoice- to verify process invoice functionality
Sc_22-tc01 - test or verify that the Invoice Date is populated with the current/system date, allows a past date, and does not allow a future date.
Sc_22-tc02To test or verify that the user can select the required Payment Terms from the available options.
Sc_22 - tc03 To test or verify that the Due Date is calculated correctly based on the selected Payment Terms and Invoice Date.
Sc_22- tc04 test or verify that clicking Process Invoice successfully processes the invoice and creates the required dispatch entry
to verify the Reference functionality
Sc_23-tc01 To test or verify that the Reference is displayed for the invoice.
Sc_23-tc02To test or verify that the Reference is automatically generated for the invoice
Back
sc_24-tc01to test the when clicked on back navigate on perivous module{refer to sc_05}
Sc_24-tc02 To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged {refer to sc_05}
update
sc_25-tc01 to test item get updated when total amount calculate and shipping charge is invalid {refer to sc_04}
sc_24-tc02 to test item get updated when total amount calculate and shipping charge is valid {refer to sc_04}
sc_24-tc03to test item get updated when total amount calculate and shipping charge is blank{refer to sc_04}

## module 6
Section 2
Supplier & Receive Into
sc_33 -tc01 To test or verify user can select required Valid section when value is correctly dropdown
Supplier's Reference
Sc_34-tc01To test or verify that the user can enter Valid alphanumeric Reference value
Sc_34-tc02To test or verify that the user can enter Blank Reference value
Deliver to
Sc_35-tc01To test or verify user enter valid address
Sc_35-tc02To test or verify user enter Blank address
Add item
Sc_36-tc01To test item get add when Item code is enterned negative and quantity,price,required delivery date are are positive
sc_36-tc02 To test item get add when quantity is enterned negative and add code,price,required delivery date are are positive
sc_36-tc03 To test item get add when price is enterned negative and add code,quantity,required delivery date are are positive
Sc_36-tc04 - To test item get add when item code,quantity ,price ,required delivery date is positive
Place order button
Sc_40-tc01 - To test or verify the place order get placed when valid Data are entered.
Sc_40-tc02 - To test or verify the process for dispatching selected item when lnvalid/Blank Data are entered.
Cancel order
Sc_41-tc01 - To test or verify the Cancel order button should clear the page and displayed back
Sc_41-tc02 - To test or verify the Cancel order button should not clear the page and not navigate back module
Back
Sc_42-tc01 - Tto test the when clicked on back navigate on perivous module
Sc_42-tc02 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged
Order Date
Sc_39-tc01 - To test or verify Purchase Order Entry date is future date
Sc_39-tc02 - To test or verify Purchase Order Entry date is default date or past date

## module 7 & module 8
update
Sc_43-tc01 - To test or verify can update This delivery data when Quantity is Equal Ordered unit
Sc_43-tc02 To test or verify can update This delivery data when Quantity is less then Ordered unit
Sc_43-tc03 To test or verify can update This delivery data when Quantity is Blank Ordered unit
Process Receive Item
Sc_44-tc01 To test or verify the Purchase get Processed when valid Data are entered
Sc_44 -tc02To test or verify the Purchase get Processed when Invalid Data are entered
Back
Sc_45-tc01 - to test the when clicked on back navigate on perivous module{ refer to sc_42}
Sc_45-tc01 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged{ refer to sc_42}
module 8
Quantity Items Received for invoice
Sc_47-tc01 - 1) To test or verify the user can enter "Qty Yet To Invoice" is equal or less than "Quantity Received"
Sc_47-tc02 - To test or verify the user can enter "Qty Yet To Invoice" is Blank "Quantity Received"
Sc_47-tc03 - To test or verify the user can enter "Qty Yet To Invoice" is Negative "Quantity Received"
Enter Invoice button
Sc_48-tc01 - To test or verify the Purchase Invoice get Processed when valid Data are entered
Sc_48-tc02 - To test or verify the Purchase Invoice get Processed when Invalid Data are entered
Add All Item
Sc_49-tc01 - To test or verify user can add all the Purchase items at once.
Tax and Update Button
Sc_50-tc01 - To test or verify Total amount gets calculate correctly when user add valid Tax charge
Sc_50-tc02 - To test or verify Total amount gets calculate correctly when user add Invalid Tax charge
Supplier's Reference
Sc_51-tc01 - To test or verify that the user can enter Valid alphanumeric Reference value { refer to sc_34}
Sc_51-tc02 - To test or verify that the user can enter Blank Reference value Turn on screen reader support{ refer to sc_34}
update
Sc_52-tc01 - To test or verify can update This delivery data when Quantity is Equal Ordered unit{refer to Sc_43}
Sc_52-tc02 "To test or verify can update This delivery data when Quantity is More then Ordered unit{refer to sc_43}
Sc_52-tc03 - To test or verify can update This delivery data when Quantity is Blank Ordered unit{refer to sc_43}
Back
Sc_53-tc01 to test the when clicked on back navigate on perivous module{refer to sc_42}
Sc_53-tc02 To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged{refer to sc_42}

## module 9
Module 9 - Supplier Payment Entry
Bank Amount
Sc_54-tc01 - Test or verify user can enter Valid Bank amount when select retailer
Sc_54-tc02Test or verify user can enter Invalid Bank amount when Customer is Retailer
This Allocation
Sc_55-tc01 - 1) To test or verify This allocation display correctly when user click on All link the total amount of field will be show
Sc_55-tc02 - To test or verify This allocation feild when user enter Negative values
Sc_55-tc03 - To test or verify This allocation feild when user enter Blank values
None
Sc_56-tc01 - 1) To test or verify This allocation field gets Blank when user click on None Button
Amount of Discount
Sc_57-tc01 - 1) To test or verify user can add discount in "Amount of Discount" when valid value will be enter
Sc_57-tc02 - To test or verify user can add discount in "Amount of Discount" when Invalid value will be enter
Amount of Payment
Sc_58-tc01 - To test or verify user can add or enter valid Payment amount value
Sc_58-tc02 - To test or verify user can add or enter Invalid Payment amount value
Enter a Payment Button
Sc_59-tc01 - To test or verify the Payment get placed when valid Payment Amount, Bank charges,This allocation , Amount and Discount are entered.
Sc_59-tc02 - To test or verify the Payment get placed when Invalid Payment Amount, Bank charges,This allocation , Amount and Discount are entered.
-

## module 10
section 3
Module 10- Inventory Location Transfers: Field Description
Date
Sc_60-tc01 -To test or verify date is accepted when Past date and present date should be selected
Sc_60-tc02 - To test or verify date is accepted when Future date should be selected
From Location & To Location
Sc_61-tc01 - To test or verify user can select differenet selection for From location & To location data
Sc_61-tc02 - To test or verify user can select same selection for From location & To location data
Items
Sc_62-tc01 - To test or verify Item gets add when Item code, Item Description, Quantity entered valid
Sc_62-tc02 - To test or verify Item gets add when Item code is kept Invalid and Item Description, Quantity entered valid
Sc_62-tc03 - To test or verify Item gets add when Item Description is kept Invalid and Item code, Quantity entered valid
Sc_62-tc04 - To test or verify Item gets add when Quantity is kept Invalid and Item code, Item Description entered valid
Process Transfer
Sc_63-tc01 - To test or verify the Process Transfer get Processed when valid Data are entered
Sc_63-tc02 -To test or verify the Process Transfer get Processed when Invalid Data are entered
Back
Sc_64-tc01 - to test the when clicked on back navigate on perivous module
Sc_64-tc02 - To test or verify that when the user clicks the Back button, the previously entered/added data remains unchanged